## Dashboard
Roadmap to Action Workbook
The purpose of this workbook is to guide the development of projects associated with resilience-enhancing solutions. This workbook will assist users in defining projects, identifying funding sources and bundling opportunities, and documenting next steps for projects without funding.
Input should be informed by the discussions and data collected in the Roadmap to Action module found on the Technical Resilience Navigator web application [link].
Navigating this Excel File
1. Review all steps in this Dashboard sheet before entering data in the Excel file. On each sheet the various data columns and headers are color-coded as follows:
Cell color coding key:
| Input | Not Input | Input Not Applicable
Regarding data entry: if pasting data from another source, or from elsewhere in this file, always use Paste Special, and paste the data as values or unformatted text. This will prevent altering any cell formatting. Regarding automatic calculation: if not running the workbook with macros enabled, please ensure that calculation of formulas is set to "Automatic." If macros are enabled, a macro will set formulas to calculate automatically upon opening the workbook.
2. Start by bringing into this Excel sheet a list of Solutions from the Solution Prioritization Excel. Only paste solutions that were selected to carry forward into Roadmap to Action. When pasting, use Paste Special and paste the data as values or unformatted text.
3. For each solution chosen to move forward, define projects and identify resources for implementation. To build out each project, answer the ‘who, what, where, when and how’ questions. The TRN Resource: Questions for Clear Project Definition can provide additional guidance when building out a project. Some information required for this tab, such as the Consequence or Vulnerability Adjustment column, can be cut and pasted from previous workbooks. Where applicable, the location where a user can find this information is noted below the column title. More than one project may be associated with each solution.
4. Consolidate all projects from Tab 2 with identified funding sources (if available and required) and identify bundling opportunities.
5. Document projects from Tab 2 without viable funding sources and the associated solutions affected. These projects have been identified as part of a comprehensive solution, and if they are not executed, the risk reduction potential or other contributions of the solution may not be realized. Identify next steps for addressing the risks associated with these projects.
6. Cut and paste projects from Tab 3 into Tab 5 and add cost estimates in Column I. Review the TRN Resource: Identify and Evaluate Potential Funding Sources from the Roadmap to Action module, and any cost estimates developed in Actions 3 and 4 in the Solution Prioritization module as a starting point for estimating project costs. If these sources do not address certain project costs, there are many helpful resources for estimating project costs listed in the module.
Projects without Funding
Funding Sources
Project Identification
Cost Estimates
Solution Prioritization Results

## 1. Solution Prioritization
1) Sort the Solution Prioritization Workbook Tab 6 by those that were identified to move forward to Roadmap to Action. 2) Copy and paste the selected solutions into this tab. When pasting, use "Paste Special" and paste the data as values or unformatted text. More than one project may be associated with each solution.
| Solution # | Solution | Calculated value | Cost category | Solution benefit potential | Desired sort order | Desired sort order and -year total cost | Carry forward to Roadmap to Action
| Do not change | [6 empty] | Choose from drop-down
| 1 | Implement friction damper | 1300000 | High | Low potential for benefit | 16 | 16_1300000 | Yes
| 2 | New conductivity controller | 110000 | Low | Low potential for benefit | 14 | 14_110000 | Yes
| 3 | Test and exercise mission duplication capability for data processing and analysis function. Improve process to reduce time required to initiate capability. | 200000 | Low | Moderate potential for benefit | 10 | 10_200000 | Yes
| 4 | Solution set: friction damper + conductivity controller + enhancement of mission duplication capability. | 1610000 | High | Moderate potential for benefit | 12 | 12_1610000 | No
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## 2. Project Identification
For each solution chosen to move forward, define projects and identify resources for implementation. To build out each project, answer the 'who,' 'what,' 'where,' 'when,' and 'how' questions. The TRN Resource: Questions for Clear Project Definition can provide additional guidance when building out a project. Some information required for this tab, such as the Consequence or Vulnerability Adjustment column, can be cut and pasted from previous workbooks.
Solution # | Solution | Project (What) | Project # | Project Location (Where) | Calculated Value | Facilities | Critical Load(s) | Consequence or Vulnerability Adjustment | Partners (Who) | Deadlines (When) | Resources (How) | Linkages to Other Projects and Priorities
Cut and paste from RTA Tab 1 Do not change | Cut and paste from RTA Tab 1 Do not change | Enter and describe project | Do not change [Solution Number, Project Number] | Location-specific information for projects (may be broader or more focused than facility in Column H) | Cut and paste from RTA Tab 1 Do not change | List facility or facilities benefiting from solution. Cut and paste from Solution Prioritization Tab 2 | List critical load(s) benefiting from solution. Cut and paste from Solution Prioritization Tab 2 | Refer to Solution Prioritization Tab 2, Column I or K | This could include internal and external stakeholder analysis | Project implementation deadline | Types of resources can include monetary, skilled personnel, and/or time | This could include similar organizational plans and priorities
1 | Friction damper | Implement friction damper | 1.01 |  | 1300000 | Building 345 | Critical mission housed in building protected during an earthquake | Vulnerability adjustment: Protection during natural disaster | Site manager, HQ lead | 2022-12-01 | Appropriated
2 | Conductivity controller | New conductivity controller | 2.01 |  | 110000 | Building 123 | Cooling for Data Center X, water for training facility | Vulnerability adjustment: Redundant system (water) qualifies for longer duration outages (1 month). | Facilities manager | 2021-12-01 | Appropriated and ESPC | Similar solutions proposed for Building 456
3 | Test and exercise mission duplication capability for data processing and analysis function. Improve process to reduce time required to initiate capability. | Mission duplication process improvement | 3.01 |  | 200000 | Building 123 | Cooling for Data Center X, water for training facility, IT plug loads for Data Center X | Consequence adjustment: Reduces time required (from 48 down to 16 hours) for initiation of mission duplication capability and increases likelihood of success (via tests and exercises). | Mission owner | 2022-03-01 | Internal agency funds/appropriated funds

## 3. Funding Sources
Consolidate all projects from Tab 2 with identified available funding sources (noted in Tab 2, Column O) and identify bundling opportunities. Projects without funding sources should be documented in Tab 4. Projects that do not require funding to move forward should be documented in this tab, as long as resources are available to support project implmentation.
Project | Project # | Solution # | Solution | Project Location | Funding Source
Cut and paste from RTA Tab 2 Do not change | Cut and paste from RTA Tab 2 Do not change | Cut and paste from RTA Tab 2 Do not change | Cut and paste from RTA Tab 2 Do not change | Cut and paste from RTA Tab 2 Do not change | List potential appropriations, performance contracting, and grant funding
New conductivity controller | 2.01 | 2 | Conductivity controller | Building 123 | Appropriated and ESPC
Mission duplication process improvement | 3.01 | 3 | Test and exercise mission duplication capability for data processing and analysis function. Improve process to reduce time required to initiate capability. | Building 123 | Internal agency funds/appropriated funds

## 4. Projects without Funding
Document projects from Tab 2 without viable funding sources and the associated solutions affected. These projects have been identified as part of a comprehensive solution, and if they are not executed, the risk reduction potential or other contributions of the solution may not be realized. Identify next steps for addressing the risks associated with these projects.
Project | Project # | Solution # | Solution | Project Location | Barrier | Resulting Unresolved Gaps or Risks | Next Steps
Cut and paste from RTA Tab 2 Do not change | Do not change [Solution Number, Project Number] | Cut and paste from RTA Tab 2 Do not change | Cut and paste from RTA Tab 2 Do not change | Cut and paste from RTA Tab 2 Do not change | Identify barriers to completing project | Identify gaps/risks that need to be resolved to obtain funding | Discuss possible solutions to obtain funding
Implement friction damper | 1.01 | 1 | Friction damper | Building 345 | Special funding will need to be appropriated for this project | Risk to mission | Complete study to show risk to mission from natural disaster

## 5. Cost Estimates
Cut and paste projects from Tab 3 into Tab 5 and add cost estimates in Column I. Review the TRN Resource: Identify and Evaluate Potential Funding Sources from the Roadmap to Action module, and any cost estimates developed in Actions 3 and 4 in the Solution Prioritization module as a starting point for estimating project costs. If these sources do not address certain project costs, there are many helpful resources for estimating project costs listed in the module.
Project | Project # | Solution # | Solution | Project Location | Funding Source | Bundle | Cost Estimate
Cut and paste from RTA Tab 2 Do not change | Cut and paste from RTA Tab 2 Do not change | Cut and paste from RTA Tab 2 Do not change | Cut and paste from RTA Tab 2 Do not change | Cut and paste from RTA Tab 2 Do not change | Cut and paste from RTA Tab 3 Do not change | Cut and paste from RTA Tab 3 Do not change | New cost estimate after going through Business Justification Worksheet
New conductivity controller | 2.01 | 2 | Conductivity controller | Building 123 | Appropriated and ESPC | Discounts available for bulk purchase of conductivity controller with Building 456 | 100000
Mission duplication process improvement | 3.01 | 3 | Test and exercise mission duplication capability for data processing and analysis function. Improve process to reduce time required to initiate capability. | Building 123 | Internal agency funds/Appropriated funds |  | 210000